## Sheet1
User Stories
US_01 | As a user, I want to an option to select a story with a theme, so that i dont have to come up with a new one | - The user can select from multiple preset stories (4) - The user can browse and select from 3-4 options in the app. - The app moves to the next step after clicking "Continue" | Preset story options (3-4) ¦ Theme Description | Story Setup | 34 | Sharon ¦ Mrun ¦ Ajla
No. | Test Case Title | Test Flow | Expected Result | Execution Status | Exectution Date | Tester
TC_01_01 | Landing Page | Starts on the landing page Click "continue" | Page loads, all information is clearly visible, routes are correct, Landing page matches design On clicking "continue", routes to theme selection page | Passed | 2025-03-08 | Dylan
TC_01_02 | Themes Page | Routes from the landing page Select a theme Click Continue | Routes from the landing page Theme page matches design All available themes are loaded from API On selection, selected theme is highlighted On clicking "continue", routes to story selection page | Passed | 2025-03-08 | Dylan
TC_01_03 | Story Page | Routes from the theme selection page Select a story Click Continue | Routes from the landing page Story page matches design All available stories for selcted theme are loaded from API On selection, selected story is highlighted On clicking "continue", routes to character description page | Passed | 2025-03-08 | Clive
User Stories
US_03 | As a user, I want to describe the character I will be playing in the story to the app | - User can enter a name for their character. - User can choose/enter attributes (e.g., personality traits, skills, background). - Character details are saved - Character details cannot be modified after starting the story. | Main (User) Character Builder Prompt ¦ Example prewritten Character prompt | Story Setup | 34 | Ajla ¦ Dhruv
TESTS
No. | Test Case Title | Test Flow | Expected Result | Execution Status | Exectution Date | Tester
TC_03_01 | Create a Character | cURL POST command simulating the frontend | The data for character and its attributes is stored in the database under its collection name | Passed | 2025-03-08 | Farham
TC_03_02 | Fetch All Characters | cURL GET command simulating the frontend | Returns all of the stored characters | Passed | 2025-03-08 | Clive
TC_03_03 | Fetch Character by Name | cURL GET command simulating the frontend | Returns all of the character with the name | Passed | 2025-03-08 | Clive
TC_03_04 | Character creation screen | Routes from the story page Enter data for the character Click create |  | Pending
User Stories
US_10 | As a user i want to experience an interactive novel where my choices dynamically shape the story | - The system tracks player decisions and adapts the story and determines different endings accordingly. - Choices made early in the game influence later events. - The game provides unique responses based on different player actions. | Dynamic Story Pivot - Single player | AI Story | 55 | Dhruv ¦ Dylan ¦ Clive
TESTS
No. | Test Case Title | Test Flow | Expected Result | Execution Status | Exectution Date | Tester
TC_10_01 | Story Adapts to Player Choices | - Start a new game session. - Make different choices in the game. - Observe how the AI responds to each decision. | - AI adapts its narration based on previous choices. - The story branches differently for different users. | Passed | 2025-03-08 | Sharon
TC_10_02 | Early Choices Affect Later Events | - Play through the game twice with different early choices. - Compare how later game events change based on the initial decisions. | - Choices from early in the game impact events and dialogue later. - Different paths emerge depending on decisions | Passed | 2025-03-08 | Sharon
TC_10_03 | AI Handles Unexpected Inputs | - Enter random, irrelevant, or unexpected inputs. - Observe how the system handles and responds. | - AI gives meaningful responses even for unexpected inputs. - System does not crash or behave erratically. | Passed | 2025-03-08 | Farham
User Stories
US_12 | As a user, I expect the AI to introduce unexpected but logical story developments. | - The AI introduces unexpected but logical events based on player choices. - The generated twists maintain continuity within the story. - Twists vary across playthroughs for replayability. | Maintain story consistency | AI story | 55 | Farham ¦ Dylan
TESTS
No. | Test Case Title | Test Flow | Expected Result | Execution Status | Exectution Date | Tester
TC_12_01 | Story Continuity is Maintained | - Start a session - Input multiple decisions - Check if generated twists maintain story coherence. | AI-generated twists do not contradict previous story elements. | Passed | 2025-03-08 | Dhruv
TC_12_02 | Logs Store AI-Generated Twists | - Input a decision - Retrieve logs from the database - Verify if AI-generated context is saved correctly | AI-generated story twists are stored in the database under the correct sessionId. | Passed | 2025-03-08 | Dhruv
TC_12_03 | Logs Retrieved Based on SessionID | - User starts a session and gets sessionId. - User inputs an action and AI processes the input and generates a story update. - Send a GET request to /api/logs/:sessionId using Postman. - Verify retrieved logs store the AI-generated twist and user input with SessionID. | Logs are correctly retrieved based on sessionId. | Passed | 2025-03-09 | Clive
User Stories
US_19 | As a user, I want to read the created story | - Created Story Text is Displayed - Can scroll through Displayed Story | Display Story History ¦ Scrollable View | Accessibility | 55 | Clive ¦ Sharon ¦ Dylan
TESTS
No. | Test Case Title | Test Flow | Expected Result | Execution Status | Exectution Date | Tester
TC_19_01 | Start Game and Display Initial Story | - Select a theme and choose a story - Start the game - Check if the first narration appears - Scroll down to see if it's readable | - The story text is shown correctly - UI auto-scrolls to the latest message | Passed | 2025-03-08 | Farham
TC_19_02 | Player Makes a Move | - Enter any valid choice in the chat box - Click Send - AI should respond with the next part | - User input appears (right-aligned) - AI response appears (left-aligned) - Auto-scroll updates chat | Passed | 2025-03-08 | Ajla
TC_19_03 | Ensure Story History Persists on Refresh | - Start a game and play a few moves - Refresh the page - Check if previous story log is still displayed | - Story history loads from localStorage/backend - UI restores previous messages | Failed | 2025-03-08 | Ajla
TC_19_04 | Scroll Functionality | - Play through a long session - Scroll up and down to verify all messages are accessible | - Story logs remain readable - Scrolling works smoothly | Passed | 2025-03-08 | Ajla
TC_19_05 | Auto-scroll Behavior on New Message | - Scroll up manually - Let AI respond - Check if it auto-scrolls to the latest message | - Auto-scroll only occurs if the user is at the bottom of the chat | Passed | 2025-03-08 | Farham