## UserStories
No. | User Stories | Acceptance Criteria | Story Points | Assigned to | Feature | Component
SPRINT 1
US_01 | As a player, I expect logical story developments so that the story is consistent to the previous interactions. | - The AI introduces unexpected but logical events based on player choices. - The generated twists maintain continuity within the story. - Twists vary across playthroughs for replayability. | 13 | Farham ¦ Dylan | Maintain story consistency | AI story
US_02 | As a player i want to experience an interactive story with dynamic choices so that I can shape the story. | - The system tracks player decisions and adapts the story and determines different endings accordingly. - Choices made early in the game influence later events. - The game provides unique responses based on different player actions. | 8 | Dhruv ¦ Dylan ¦ Clive | Dynamic Story Pivot - Single player | AI Story
US_03 | As a player, I want to select a theme, so that i have a general setting for the story i want to play. | - The user can select from multiple preset themes (3) - The user can browse and select options in the app. - The app moves to the next step after clicking "Continue" | 5 | Sharon ¦ Ajla | Preset Theme options (3-4) ¦ Theme Description | Story Setup
US_04 | As a player, I want to select a story within a theme, so that i dont have to come up with a new one | - The user can select from multiple preset stories (4) - The user can browse and select from 3-4 options in the app. - The app moves to the next step after clicking "Continue" | 5 | Sharon ¦ Ajla | Preset story options (3-4) ¦ Theme Description | Story Setup
US_05 | As an admin user, I want to create a theme, so that users can browse stories within a selected theme | - The user can create one theme at a time with title, description, and cover image - The user can view and edit created themes | 1 | Dylan ¦ Sharon
US_06 | As an admin user, I want to create a story within a theme, so that users can browse and select the latest story | - The user can create one story at a time with title, description, duration, narrator tone and theme - The user can view and edit created stories | 2 | Clive ¦ Sharon ¦ Dylan
US_07 | As a player, I want to read the created story so I can refer to my past actions | As a user, I want to read the created story | 3 | Clive ¦ Sharon ¦ Dylan | Display Story History ¦ Scrollable View | Accessibility
SPRINT 2
US_08 | As a player, I want to personalize the character I will be playing in the story so that I can have more control over my protagonist. | - User can enter a name for their character. - User can choose/enter attributes (e.g., personality traits, skills, background). - Character details are saved - Character details cannot be modified after starting the story. | 5 | Ajla ¦ Dhruv | Main (User) Character Builder Prompt ¦ Example prewritten Character prompt | Story Setup
US_09 | As a player, I want detailed environmental descriptions and character emotions in my story, so I am more attuned to the story. | - AI dynamically generates detailed environmental settings. - Scene descriptions adapt to past user actions, mood, and themes. - Character emotions and NPC expressions are included in the narration. | 2 | Ajla | Using descriptive models with a larger parameter count. | AI story
US_10 | As a player, I would like to know when I have reached the game's conclusion of the game so that I know I have reached the end of the session. | - Show some form of clear display of the novel ending - Mention story needs to eventually end in the prompt to begin story - Have a clear splash screen depicting story has ended - Disable any input fields | 8 | Clive ¦ Sharon | End Game Prompt | Game Mechanics
US_11 | As a player, I want to interact with other non playable characters as an active part of the story so I can have additional members to interact with. | - NPCs appear throughout the story - Can dynamically interact with NPCs | 8 | Farham | Preset NPCs ¦ Dynamic NPC inclusion | Game Mechanics
US_12 | As a player, I want my character’s actions to be determined by a dice roll so there is unpredictablitiy in outcomes | -The system rolls a virtual die when an action requires a success/failure check. -The game clearly displays the roll result and its impact on the story. -The system assigns success probabilities dynamically for custom inputs. -The probability of success/failure is determined by who is rolling the dice. | 5 | Dylan ¦ Farham | Dice Roll | Game Mechanics
US_13 | As a an admin user, I want to add interesting yet feasible NPC's that fit the storyline into the preset so that the player can have additional NPCs to interact with throughout the stroy. | - Introduce NPC characters into the storyline preset text -Write a story wrtiing prompt with description of variations in NPC's to interact with in the story (Add on to Preset Feature) | 5 | Sharon ¦ Dylan | Preset NPCs ¦ Dynamic NPC inclusion | AI Story
US_14 | As a player, I want to listen to the story, so that I can have an immersive experience | - The user can toggle Voice button to listen to the story generated. | 2 | Dhruv | Text-to-Speech | Accessibility
US_15 | As a player, I want to receive clear feedback so I know when my dice roll has passed or failed. | -Color distinction of green or red to see impact of desicion | 5 | Dylan ¦ Clive ¦ Farham | Impact Feedback | Accessibility
US_16 | As a player, I want to choose the number of players so we can explore adventures together | - The user is prompted with player "Single Player" or "Multiplayer" - The system allows players to create and name their own characters. - Each player can customize character attributes, such as role, stats, or abilities. - The game supports multiple characters within a single session. | 8 |  | Multiplayer Game Option | Story Setup
US_17 | As a player, I want the app to play my favorite novel as a story when I enter the novel's name, so that i can dive in without describing the entire novel | - The user is prompted with "Story" and "Novel" option. - The user can select the "Novel" Option. - The user is prompted to enter the Novel name and author. - The app presents user with options(if more than 1 is available). - The user selects the novel they want. - The app moves to the next step after clicking "Continue" | 5 |  | Play an actual Novel Story | Story Setup
US_18 | As a player, I want to interact with the game with voice controls, so that i can have an immersive experience | - The user can toggle Microphone button and speak their response when prompted to make a choice to proceed or simply type in their response in the promt area. | 5 |  | Speech-to-Text Options | Accessibility
US_19 | As a user, I want the app to dynamically adapt to me and my friends choices, while keeping the story interesting | -Ai generates logical consequences to the choices made. - All players can make their own unique choices in the provided text field -The system processes custom inputs and responds dynamically based on context. -The app ensures that user-defined actions do not break story progression. | 8 |  | Dynamic Story Pivot - Multiplayer | Game Mechanics
US_20 | As a player, I want to determine which player goes next so I can choose who make the next interaction in a multiplayer game | -The system cycles through each user for their prompts | 3 |  | Player Turns | Game Mechanics
US_21 | As a player, I want to customize the UI like font size and color adjustments, so that I can comfortably read the text. | - Users can increase or decrease font size. - Users can switch between dark mode and light mode. | 3 |  | Limited Customization to UI (Font, Background Theme) | Accessibility
US_22 | As a player, I want the game to have graphics and animations which enhance the storyline so that I can have a more visual experience | - The graphics are visually consistent with the game's style and theme. | 13 |  | Visuals and Sound | Accessibility
US_23 | As a player, I want to be able to generate the image of the context, so that I can see what my protagonist is looking at. | - View NPC characters in the storyline preset text - Display variations in NPC's to interact within the story | 2