## CompletedNotCompleted
No. | User Stories | Assigned to: | Completed Date | Story Points | Completed Points
No. | User Stories | Assigned to: | Completed Date | Story Points | Completed Points
US_10 | As a player, I would like to know when I have reached the game's conclusion of the game so that I know I have reached the end of the session. | Clive | 2025-05-03 | 2 | 2
| Hypothesize Methods for ending game |  | 2025-03-31
| Discuss and Select one method for this sprint completion |  | 2025-03-31
| Develop selected Method of ending game to trigger Open AI to end game when goal is achieved |  | 2025-05-01
US_14 | As a player, I want to listen to the story, so that I can have an immersive experience | Dhruv | 2025-05-03 | 1 | 1
| Import text to speech library |  | 2025-03-31
| Use text to speech on context generated |  | 2025-03-31
| Frontend button to initiate text to speech for context |  | 2025-03-31
US_16 | As a player, I want to choose the number of players so we can explore adventures together | Farham | 2025-05-01 | 5 | 5
| Design player selection UI for entering number of players |  | 2025-04-30
| Create frontend logic to display forms based on number of players |  | 2025-04-30
| Add validations (min/max players, non-zero input) |  | 2025-04-30
US_17 | As a player, I want the app to play my favorite novel as a story when I enter the novel's name, so that i can dive in without describing the entire novel | Optional | - | 5 | 0 | Not completed
| Create frontend input for novel title entry |  | -
| Build backend endpoint to handle novel name |  | -
| Test a set of popular novels and tune prompt generation for consistency |  | -
US_18 | As a player, I want to interact with the game with voice controls, so that i can have an immersive experience | Dhruv | 2025-05-03 | 8 | 8
| Research and integrate browser-compatible speech recognition library |  | 2025-05-01
| Add mic input button on main interaction screen |  | 2025-05-02
| Convert voice input to text and pass to existing input handler |  | 2025-05-02
US_19 | As a user, I want the app to dynamically adapt to me and my friends choices, while keeping the story interesting | Dylan | 2025-05-01 | 13 | 13
| Change /play-turn endpoint to accept an array of playerChoices |  | 2025-04-25
| Modify Log structure to handle multiple player inputs per turn |  | 2025-04-25
| Enhance OpenAI prompt to handle multiple players |  | 2025-04-27
| Test with 2–3 players |  | 2025-04-27
| Single-player backward compatibility |  | 2025-04-27
US_20 | As a player, I want to determine which player goes next so I can choose who make the next interaction in a multiplayer game | Dylan | 2025-05-01 | 8 | 8
| Add player selection dropdown after each interaction |  | 2025-04-29
| Implement backend logic to track and update the current player's turn. |  | 2025-04-29
| Create API endpoints to get and set the active player |  | 2025-04-29
| Notify selected player it's their turn via UI/animation |  | 2025-04-29
US_22 |  | Farham | 2025-05-01 | 8 | 8
| Create S3 Bucket |  | 2025-04-24
| Implement upload logic from backend to S3 bucket |  | 2025-04-27
| Fix NPC Schema to hold Image URLS. |  | 2025-04-27
| Modify Prompt output to have Context + Json section for toggle |  | 2025-04-28
| Modify prompt to toggle NPC activation when in scene |  | 2025-04-29
|  |  |  | 50 | 45